## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Sultans of Scrum
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper/buyer I want to see a list of needs and so that I choose what to contribute to and purchase for the foundation and/or my own pet. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page to view the needs of the foundation. Given I log in with a username that is not "admin" , when I am in the helper dashboard, then I I must see the list of available need in the foundation | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25
As a helper I want to add and remove needs from my private funding basket so that I can checkout needs and keep track of them | Given that I am in the helper dashboard, when I click the add need button then I can add needs to my funding basket. Given that I am in the funding basket page, when I click the delete button , then I the need will be removed from my funding basket. Given I am looking at the detailed view of my need, when I want to add a need to my basket, then I must have a way to add that need into my funding basket | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25
As a helper I want to search for needs so that I can choose what to contribute to. | Given that I am in the helper dashboard, when I look for a need in the search bar, then I can see if the organization has a need that I can purchase | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25
As a helper I want to have an option to login as a "Helper/Buyer" so that I can support the foundation and/or buy a product for my own pet | Given I am in the login page, when I have the username that is not "admin" and click the submit button, then I can login into the helper dashboard to access the needs of the organization I want to help | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25
As a helper I want to have a private funding / purchase basket that only I can see and which stays consistent unless I change it, so that I can keep track of what I would like to purchase. | Given that I am in the helper dashboard, when I want to view the needs in my funding basket, then I should be able to access that view | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25
Pass
As a U Fund Manager I want to see a list of the needs/products of my foundation so that I can easily keep track of what helpers can support. | Given that I login as an "admin" when I access the dashboard then I can see a list of the needs my foundation has in the cupboard | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25
As a U Fund Manager I want to have the option to login as an Admin so that I can manage my needs and access the system. | Given I am in the login page, when I have the username of "admin" and click the submit button, then I can login into the admin dashboard to access the system and manage my needs | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25
As a U Fund Manager I want to add, edit and remove needs from my cupboard so that I can have control over the inventory of needs | Given I am in the Admin Dashboard when I click the update button then I will be able to update my need. Given I am in the Admin Dashoard, when I click on the add need button in the navigation bar then I will be able to add a new need to the foundation's cupboard. Given I am in the Admin Dashboard, when I click the delete need button then the need will be removed from my foundation's cupboard. Given that I want to add a need to the cupboard, when I dont fill out all the fields , then the need wont be added and I will return to the dashboard | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CL 10/25 ¦ CZ 10/25
As a U Fund Manager I want to log out of U Fund website | Given I am in any page of the website, when I click the log out button I want to exit the website and return to the login page | Pass | MD 10/25 ¦ RA 10/25 ¦ CL 10/25 ¦ CZ 10/25