## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-10-a Sultans of Scrum
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Khoi Pham; date; comments (required if test failed) | Tester initials; date; comments (required if test failed) | Bryant Cheng
As a helper/buyer I want to see a list of needs and so that I choose what to contribute to and purchase for the foundation and/or my own pet. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page to view the needs of the foundation. Given I log in with a username that is not "admin" , when I am in the helper dashboard, then I I must see the list of available need in the foundation | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS | JAD; PASS | pass and pass
As a helper I want to add and remove needs from my private funding basket so that I can checkout needs and keep track of them | Given that I am in the helper dashboard, when I click the add need button then I can add needs to my funding basket. Given that I am in the funding basket page, when I click the delete button , then I the need will be removed from my funding basket. Given I am looking at the detailed view of my need, when I want to add a need to my basket, then I must have a way to add that need into my funding basket | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; When you add multiple instances of the same need and then delete one of them, it deletes all the needs. | JAD; PASS - Maybe show success message for adding to basket | pass and pass and pass
As a helper I want to search for needs so that I can choose what to contribute to. | Given that I am in the helper dashboard, when I look for a need in the search bar, then I can see if the organization has a need that I can purchase | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS, although I recommend making the search bar case sensitive :D | JAD; PASS | pass
As a helper I want to have an option to login as a "Helper/Buyer" so that I can support the foundation and/or buy a product for my own pet | Given I am in the login page, when I have the username that is not "admin" and click the submit button, then I can login into the helper dashboard to access the needs of the organization I want to help | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 ¦ GG 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS | JAD; PASS | pass
As a helper I want to have a private funding / purchase basket that only I can see and which stays consistent unless I change it, so that I can keep track of what I would like to purchase. | Given that I am in the helper dashboard, when I want to view the needs in my funding basket, then I should be able to access that view | Pass | MD 10/25 ¦ RA 10/25 ¦ CZ 10/25 ¦ CL 10/25 |  | JL; 11/09/23; Funding basket does not save after logging out | KP; 11/09/23; PASS | JAD; PASS - Maybe save quantity of Needs edited by Helper | pass
Pass
As a U Fund Manager I want to see a list of the needs/products of my foundation so that I can easily keep track of what helpers can support. | Given that I login as an "admin" when I access the dashboard then I can see a list of the needs my foundation has in the cupboard | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS | JAD; PASS | pass
As a U Fund Manager I want to have the option to login as an Admin so that I can manage my needs and access the system. | Given I am in the login page, when I have the username of "admin" and click the submit button, then I can login into the admin dashboard to access the system and manage my needs | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CZ 10/25 ¦ CL 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS | JAD; PASS | pass
As a U Fund Manager I want to add, edit and remove needs from my cupboard so that I can have control over the inventory of needs | Given I am in the Admin Dashboard when I click the update button then I will be able to update my need. Given I am in the Admin Dashoard, when I click on the add need button in the navigation bar then I will be able to add a new need to the foundation's cupboard. Given I am in the Admin Dashboard, when I click the delete need button then the need will be removed from my foundation's cupboard. Given that I want to add a need to the cupboard, when I dont fill out all the fields , then the need wont be added and I will return to the dashboard | Pass | MD 10/25 ¦ RA 10/25 ¦ GG 10/25 ¦ CL 10/25 ¦ CZ 10/25 |  | JL; 11/09/23; Need Quantity can be 0 or negative | KP; 11/09/23; PASS, although I think you should implement it so then the need quantity can be 0. | JAD; PASS - Currently you can edit the names of Needs to have duplicate names | pass(with a few bugs, can update with invalid values, 0 and negatives) and pass and pass. when fields aren't filled in page gives "please fill out every input"
As a U Fund Manager I want to log out of U Fund website | Given I am in any page of the website, when I click the log out button I want to exit the website and return to the login page | Pass | MD 10/25 ¦ RA 10/25 ¦ CL 10/25 ¦ CZ 10/25 |  | JL; 11/09/23; PASS | KP; 11/09/23; PASS | JAD; PASS | Pass
|  | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13 |  |  |  |  | Add a Admin search bar so that admin can
As a Unregistered User I want to use the sign in feature so that I can be registered in the system | Given A user on the login page when I click sign up button then I get redirected to a sign up page, Given A user on sign in page when they input an new username then I am registered with the system and redirected to my dashboard, | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As a Admin I want my needs to be stored when I delete it so that it is not deleted indefinitely. | Given a helper checks out their funding basket when the needs are deleted from the cupboard then I expect the needs to be stored in a file. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As an ADMIN I want to UPLOAD an image so that the users have a nice photo to look at. | Given an Admin is logged in on the add needs page, when they click on add image then it should be saved to our repository | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given an Admin has already added a file, when they press select file again then they should be able to choose a new image. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As a Potential Adopter, I want to be able to select some pet profiles that go in a favorites list for later viewing of pets I might like to adopt. | Given a helper is on the browse pets page when they click add to favorites then the pet should be stored in the users favorites list. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given a helper is logged into their favorites list, when they click remove then the pet listing is removed from their favorites list. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given a helper is logged in with listings in their favorites list, when they log out then their data should be saved and displayed next time they log in | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As a Buyer I want to checkout with the needs I have in my funding basket so that the organization can receive my donation. | Given I am a helper with needs in my funding basket, when I navigate to checkout then I should be able to see all the needs within my basket. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given I am a helper with needs in added to my basket when I navigate to the checkout page and hit checkout then all the needs are removed from my basket and the website is updated. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As a product Owner, I want to add / remove / edit pet profiles to reflect which animals are still adoptable so that all pets get a chance at adoption and customers are kept up to date. | Given an admin is logged in on the browse pets page when they click on the delete button, then the listing should be deleted | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given an admin is logged in on the browse pets page when they click on the update button then they should be prompted for new data to enter for the listing. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given an admin is logged into our website, when they click on add pet then they should be prompted for information for the new pet listing. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
As a Potential Adopter, I want to see images and names of the pets as well as adoption information so that I can choose which one to adopt, if any. | Given a helper is logged in when they navigate to the browse pets page then they should see all the listings for pets we have with small descriptions. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/13
| Given a helper is on the browse pets page when they click on a pet then they should be shown the pets details page to get all the information about the pet listing. | Pass | MD 11/13 ¦ RA 11/13 ¦ CL 11/13 ¦ CZ 11/23